## Sheet1
Total Duration:60 Hrs
Activity/Component | Technologies/Tools used | Duration(in Hours) | Support provided by Trainer | Deliveries Expected from Associates | Evaluation Process | Remarks
Case Study Discussion & High Level Design. Briefing Technologies/Tools to be used. Identification of Associate's Skill Gaps(if any) |  | 3 | FullFilling Skill Gaps, Support Associates when Associates are Blocked, Guiding in dev. Of sample Use Case | List of REST WebServices exposed, input/output to each WebService EndPoint.
Mid Tier(Design Patterns, apply) | Spring Core/Boot[2], Spring MVC, Microservices[9], Spring Security/Caching[10], Authentication, Web Token[10], Junit/Mockito[8], PostMan Tool, Maven[3], GIT[6] | 8 |  | Implementation of REST Controller using Spring Boot, MVC, interaction with Service, Development of Service Layer. Unit Test using Junit/Mockito, since DAO Layer doesn't exist they can be Mocked. Screenshots. |  | Since Associates are familiar with these Technologies, only 8 Hrs is allocated for the same. Source code can be developed by associates
| RabbitMQ[15] | 1 |  | Demo/ScreenShots
| Apigee[15] | 1 |  | Demo/ScreenShots
Backend | Spring Data/JPA & Hibernate[8], MySQL DB, Maven, GIT, | 9 |  | Unit Tested(using Junit/Mockito)DAO Layer(DAO interfaces, implementation) DAO implementation need to interact with Hibernate using Spring Data. Necessary Mappings need to be used. Integrated with REST Controller Web Services. Screenshots.
Front End | HTML5, CSS3, Bootstrap, JavaScript, Jquery, Angular 6[9], React/Redux[14], Maven, GIT | 20 |  | Wireframes, Routing for Navigation purpose, Components, Templates, AJAX. Screenshots.
Integration Testing? |  | 1
Dev Ops(CI/CD) | CI/CD, Jenkins[6], Docker[9], Kubernetes[13], AWS[13] | 7
| Jenkins |  |  | Demo/Screenshots (scripts, if used)
| AWS |  |  | Demo/Screenshots
| Kubernetes |  |  | Demo/Screenshots
| Total Duration | 50
Evaluation Criteria of Deliverables

## Sheet2
User Table | User MicroService | i/p | o/p | Other MicroService(s) to be invoked | remarks | Other Instructions
id | getUser | id | UserDetails |  |  | In DB, Data may be duplicated, if there is a need, as suggested by NoSQL databases
username(email id) | login |  |  |  |  | One MicroService can invoke other MicroService, or MicroService can be invoked from Client, directly
password(hashed) | signup
first name | confirmUser
lastname | blockUser
contact number
reg_datetime(automatic current date)
reg_code(automatic code registrtn for each course the user register) link with mentor table
active
Mentor Table | Search MicroService | i/p | o/p | Other MicroService(s) to be invoked
id | getSearchResults | Skill name, time slot | SearchResults(Trainer name, time slot) | searchSkills[only once] or getSkill[multiple times] | When processing this searchSkills MicroService need to be invoked, to get all Skills details
username(email id) | getMentorDetails | mentor_id | Mentor including MentorSkills, MentorCalendar(optional) |  | This may need to be invoked from client, when user clicks on a SearchResult, of a specific Trainer
linkedin_url
reg_datetime(automatic current date)
reg_code(automatic code registrtn for each course the mentor register)
years_of_experience
contact
active
password
MentorSkills Table
id (link to mentor table)
mid
sid
self_rating
years_of_exp
trainings_delivered
facilities_offered
MentorCalendar Table
id(link to mentor table)
mid
start_time
end_time
start_date
end_date | Skills MicroService | i/p | o/p(JSON)
| getSkill | id | Skill
Technologies/Skills Table | searchSkills | searchString | Matching skills array |  | If search string is empty retrieve all Skills
id
Name
TOC
Duration
Prerequites
| Trainings MicroService | i/p | o/p(JSON)
| getCompletedTrainings | username or user_id | List of Trainings objects | getMentor, getUser, getSkill
Trainings Table | getUnderProgressTrainings | username or user_id | List of Trainings objects | getMentor, getUser, getSkill
id | createTraining |  | Training object which got created
user_id | proposeTraining, approveTraining | training_id | Training object with changed state
mentor_id | finalizeTraining | training_id | Training object with changed state & including payment details
skill_id | getTrainingDetails | training_id | Training object
status, progress, rating, start_date, end_date, maybe start_time, end_time, amount_received
Payments Table(Payments of mentor)
id
mentor_id
training_id
txn_type
amount
datetime
remarks
Admin Table
id
username
password(hashed)

## Sheet3
Algorithm for Progress & Mentor's Payment update -- Cron job Training progress today = ((todays date & time - start_date)/(end_date - start_date))*100; [[adjust time mapping]]== tp retrieve progress as of yesterday== yp if(yp is not between 25.0 and 25.99 && tp is between 25.0 and 25.99)//repeat for 50, 75, 100 { update Payment table 25% of payment to mentor } update todays progress in Trainings table ---------------------------- Whether Cron job can direclty interact with DAO or thru Microservices? Time mapping - 24 hrs to 12 mins?